## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## ProductBacklog
Product Backlog - Election Machine
User Stroy | Story Point(s) | Priority
As an admin, I need to be able to edit the questions | 3 | 4 | Medium | High | Low
As an admin, I need to be able to delete the questions | 3 | 4 | 3 | 5 | 1
As an admin, I need to be able to add the questions | 3 | 4
As a admin, Im able to log in | 3 | 5
As a User, Im able to answer questions | 4 | 5
As a User, Im able to see most suitable candidate for me | 5 | 5
As a candinate i can register for voting | 3 | 3
As a registered candidate, I want to be able to change my personal information | 4 | 3
As a registered candidate, I should be able to login | 3 | 3
As a registered candidate, I want to be able to change my answers and delete answers | 4 | 3
As a user, im able to see all candidates | 2 | 5

## sprint_planning_meetings
Spring Planning | Participants
Week 13 | Lauri | Juha | Miska
Location | Online | Online | Online | If physically present mark X
2022-03-28
Week 14
Location | Online | Online | Online
2022-04-05
Week 14
Location
Date
Week 15
Location
Date
Week 16
Location
Date
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## sprint_backlog_sprint1 (2)
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Main Tasks
Task: Mysql database configuration | 2 | Lauri | done | 2 | 0 | 0 | 0 | 0
Task: Website Layout | 4 | Juha | done | 3 | 2 | 0 | 0 | 0
User Story #1 Admin log in
Task: Admin log in form | 1 | Lauri | done | 0 | 2 | 0 | 0 | 0
Task Admin database table | 1 | Lauri | done | 1 | 0 | 0 | 0 | 0
Task: Admin Log in script | 1 | Lauri | done | 0 | 2 | 0 | 0 | 0
User Story #3 Admin deleting questions
Task: Deleting form | 1 | Lauri | done | 0 | 0 | 2 | 1 | 0
Task: Delete question script | 1 | Lauri | done | 0 | 0 | 2 | 1 | 0
User Story #3 Admin Add Questions
Task: Add Question form | 1 | Lauri | done | 0 | 0 | 0 | 2 | 1
Task: Add Question script | 1 | Lauri | done | 0 | 0 | 0 | 2 | 1
User Story #5 Admin edit Questions
Task add edit added questions script | 1 | Lauri | done | 0 | 0 | 0 | 1 | 2
User Story #6 User can see all Candidates
Task: page for seeing all candidates | 2 | Miska | done | 0 | 2 | 0 | 0 | 0
Task: Script to get all candidates from database | 2 | Miska | done | 0 | 2 | 0 | 0 | 0
User Story #7 User can answer questions
Task: Page for answering all questions | 2 | Miska | done | 0 | 0 | 2 | 0 | 0
Task: Script for reading users answers | 2 | Miska | done | 0 | 0 | 2 | 0 | 0
User Story #8 User can see most suitable candidate
Task: Page for showing most suitable candidates | 2 | Miska | done | 0 | 0 | 0 | 2 | 0
Task: Logic for deciding the most suitable candidate | 3 | Miska | done | 0 | 0 | 0 | 3 | 2
TOTAL |  |  |  | 6 | 6 | 4 | 7 | 4

## sprint_backlog_sprint1 (3)
Sprint Backlog : Sprint 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Admin add candidates
Script | 2 | Lauri | Done | 0 | 0 | 1 | 1 | 1
form | 2 | Lauri | Done | 0 | 0 | 1 | 1 | 1
Admin remove candidates
form | 2 | Lauri | Done | 2 | 1 | 0 | 0 | 0
Script | 2 | Lauri | Done | 2 | 1 | 0 | 0 | 0
Admin edit candidates
form | 2 | Lauri | Done | 0 | 0 | 1 | 1 | 1
Script | 2 | Lauri | Done | 0 | 0 | 1 | 1 | 1
Bug fixing
Fix bugs caused by new additions | 3 | Miska | Done | 0 | 0 | 0 | 1 | 2
fixed frontend bugs | 2 | Juha | Done | 0 | 0 | 0 | 2 | 0
TOTAL |  |  |  | 4 | 2 | 4 | 7 | 6